## Summary
ACTION ITEM TRACKER
Project Nordenvik — Cross-Border Acquisition ¦ Tax structure workstream ¦ Owner: Hargrove & Lund LLP (lead: N. Osei-Mensah)
Status legend
| Open | Not started / in progress
| Critical | Blocking; pre-closing or high-value
| Complete | Done
| Deferred | Phase 2 / post-close Year 2+
Workstream summary
| Workstream | Items | Critical | Open | Deferred | Owner
| Pre-closing structuring & model | 8 | 5 | 3 | 0 | Osei-Mensah / Hargrove-Szymanski
| German §8c & merger (Step 5) | 6 | 3 | 3 | 0 | Flossbach & Steinberg / Subramaniam
| Dutch fiscal unity & BV substance | 7 | 3 | 4 | 0 | Van Steenbergen / van der Hoeven
| Singapore incentive | 4 | 1 | 2 | 1 | Rajah & Tann / Group Tax
| Transfer pricing | 5 | 1 | 3 | 1 | KPMG / Group Tax
| RWI / SPA / indemnities | 4 | 2 | 2 | 0 | Hargrove & Lund / Deal team
| DAC6 & reporting | 3 | 1 | 2 | 0 | Hargrove & Lund / LU & NL counsel
| Phase 2 (Irish IP / Pillar Two) | 5 | 0 | 0 | 5 | Hargrove-Szymanski / Advisors
TOTAL
See 'Action Items' tab for the full register with owners, deadlines, dependencies, and source references. Items are keyed A-001 etc. and mapped to the Tax Structure Memorandum and Tax Cost Model.

## Action Items
ACTION ITEMS — DETAILED REGISTER
Pre-closing (P), At/Post-closing (C), Phase 2 (P2). Status: Open / Critical / Complete / Deferred. Sorted by priority then deadline.
# | Workstream | Action item | Owner | Deadline | Status | Priority | Phase | Dependency | Source ref
A-001 | Pre-close structuring | Correct financial model: Singapore 5%→17% (Pioneer expired 31 Dec 2023); re-underwrite IRR/MOIC and ETR | V. Hargrove-Szymanski / Deal Analytics | Pre-SPA signing | Critical | High | P | A-002 | Doc 4/5; Doc 10; Doc 3
A-002 | Pre-close structuring | Correct financial model: Swedish interest disallowance using standalone EBITDA (SEK 380–420M) not consolidated; model SEK 2–14M/yr disallowance | V. Hargrove-Szymanski / Deal Analytics | Pre-SPA signing | Critical | High | P | A-001 | Doc 7 §4.6; Doc 5 structural note
A-003 | Pre-close structuring | Decide debt placement: adopt Option A (retain €155M at BidCo NL; offset vs BV royalty via fiscal unity) per Doc 7 §4.7 | Osei-Mensah / Hargrove-Szymanski | Pre-closing | Critical | High | P | A-101; A-201 | Doc 7; Debt Sourcing tab
A-004 | Pre-close structuring | If partial SE pushdown required, cap SE intercompany interest at ~SEK 100–110M to preserve standalone-EBITDA headroom | Osei-Mensah / van der Hoeven | Pre-closing | Open | High | P | A-003 | Doc 7 §4.7.2
A-005 | Pre-close structuring | Confirm acquiring fund identity (Meridian IV vs 'MonteCedro Partners Fund III' per Doc 5 App A) — reconcile SPA parties | Osei-Mensah / Deal team | Pre-SPA execution | Critical | High | P | - | Doc 1; Doc 5 App A
A-006 | Pre-close structuring | Reconcile legal entity register across Doc 2/3/5 with Group Legal (operating subs: DE/SG/UK/Norway/Finland/IP AB/US) | Subramaniam / Group Legal | Pre-closing | Open | High | P | - | Doc 2; Doc 3; Doc 5
A-007 | Pre-close structuring | Confirm Nordenvik BV actual headcount & roles (4 vs 3.5 vs 8 FTE across docs) — drives substance remediation | van der Hoeven / Group HR | Pre-closing | Open | Medium | P | A-202 | Doc 9; Doc 2; Doc 5
A-008 | Pre-close structuring | Confirm LTM EBITDA definition (SEK 464M vs 478M) and intercompany loan principal to Germany (€52M vs €42M) | Deal Analytics / CFO Malmberg | Pre-closing | Open | Medium | P | - | Doc 4/5/7/8
A-101 | German §8c / merger | Commission Stille Reserven (hidden reserves) valuation of Nordenvik Deutschland GmbH domestic assets — determines preservation of €24M losses (€3.8M) | Flossbach & Steinberg (F&S) | By 15 May 2025 (pre-SPA ideal) | Critical | High | P | - | Doc 8 §3.5; EY Priority 1
A-102 | German §8c / merger | Negotiate SPA Tax Deed mechanism (escrow/indemnity/PPA) for §8c loss exposure pending Stille Reserven outcome | Hargrove & Lund / Deal team | Pre-SPA execution | Critical | High | P | A-101 | Doc 1 Sch.7; Doc 8 §3.5
A-103 | German §8c / merger | Consider binding ruling (verbindliche Auskunft) on §8c(1) Satz 6 — note 4–6 month Munich processing time | F&S | Pre-closing | Open | Medium | P | A-101 | Doc 8 §3.5
A-104 | German §8c / merger | Model §22 UmwStG 5-year lock-up impact on exit timing; add 'early exit <2030' toggle to financial model (potential €26–33M retroactive tax) | Osei-Mensah / Subramaniam | 31 May 2025 | Critical | High | C | A-105 | Doc 24 §4.4 (gap)
A-105 | German §8c / merger | Amend integration plan to flag §22 UmwStG lock-up; calendar expiration vs 5-yr hold; brief IC | Subramaniam / Osei-Mensah | 31 May 2025 | Open | High | C | A-104 | Doc 24 §4.4
A-106 | German §8c / merger | Do NOT file §8d KStG election — Step 5 merger triggers forfeiture (§8d(2) Satz 2 Nr.4) | F&S | At closing | Open | High | C | - | Doc 8 §3.7
A-201 | Dutch fiscal unity | Prepare & file Dutch fiscal unity application (BidCo + Nordenvik BV) — file within 3 months of desired effective date (target 1 Apr 2025 → by 1 Jul 2025) | Van Steenbergen / van der Hoeven | By 1 Jul 2025 | Critical | High | C | A-202; A-203 | Doc 9 §4; Doc 24 §3
A-202 | Dutch substance | Remediate Nordenvik BV substance: hire 3–5 senior IP/commercial FTEs in Amsterdam; ≥1 senior w/ decision authority; quarterly NL board meetings w/ minutes | Group Tax / HR | By 30 Jun 2025 | Critical | High | C | A-007 | Doc 9 §2.4; Doc 24 §3.3
A-203 | Dutch substance | Renew expired APA (royalty rates) with Belastingdienst — file by 30 Jun 2025 alongside fiscal unity; use KPMG arm's-length range 3.5–5.8% | Van Steenbergen / KPMG | 30 Jun 2025 | Critical | High | C | A-301 | Doc 9; Doc 24 §3.3
A-204 | Dutch substance | Build BidCo substance (local directors, office, documented decision-making) to defend PPT on SE→NL dividend flow | Legal / Group Tax | Q1–Q2 2025 | Open | Medium | C | - | Doc 5 §7.2; Doc 24 §3.4
A-205 | Dutch substance | Assess Dutch Innovation Box (9%) as alternative to Irish KDB — requires S&O-verklaring & nexus analysis | van der Hoeven | 31 Aug 2025 | Open | Medium | C | A-202 | Doc 24 §5.3; Doc 6
A-206 | Dutch fiscal unity | Confirm per-element fiscal unity availability through Swedish intermediate (Nordenvik Group AB) per CJEU X Holding / Art.15 CITA | Van Steenbergen | By 15 May 2025 | Open | High | C | - | Doc 3 §III; Doc 9 §4
A-207 | Dutch substance | Obtain annual Certificates of Residence (COR) for Nordenvik BV to support SG-NL 0% royalty WHT | Van Steenbergen | Annual (from YA2025) | Open | Medium | C | - | Doc 10 §4.4
A-301 | Singapore incentive | File ECI for FY2024 at 17% standard rate (due 31 Mar 2025); correct any Pioneer-rate filings | Rajah & Tann / SG finance | 31 Mar 2025 | Critical | High | C | - | Doc 10 §3.5
A-302 | Singapore incentive | Assess & prepare Development and Expansion Incentive (DEI) application to EDB (5%/10% concessionary; 6–12 mo process); build SG investment commitments into integration plan | Rajah & Tann / Group Tax | Q3 2025 | Open | High | C | A-006 | Doc 10 §3.6
A-303 | Singapore incentive | Maintain SG tax residency: board meetings & strategic decisions in Singapore; document minutes; caution on non-resident directors | Rajah & Tann / SG mgmt | Ongoing | Open | Medium | C | - | Doc 10 §2.3
A-304 | Singapore incentive | Evaluate IP Development Incentive (IDI) if SG R&D activities undertaken | Rajah & Tann | FY2026 | Deferred | Low | P2 | - | Doc 10 §3.6
A-401 | Transfer pricing | Adopt KPMG updated TP study (Doc 11) as single source of truth for royalty/loan rates; reconcile conflicting rates across docs | Group Tax / KPMG | Q1 2025 | Critical | High | P | A-006 | Doc 11; Doc 2; Doc 5
A-402 | Transfer pricing | Commission post-acquisition master file & local files tailored to new structure (DE, NL, SG, SE) | KPMG / local advisors | Q3 2025 | Open | High | C | A-401 | Doc 8 §6; Doc 5 §7.2
A-403 | Transfer pricing | Refresh royalty benchmark study (current 2018 study stale); confirm arm's-length range & DEMPE alignment | KPMG | Q3 2025 | Open | High | C | A-401 | Doc 2 §V.A; Doc 11
A-404 | Transfer pricing | Implement travel-tracking policy for Nordenvik BV personnel (DE/SE) to mitigate PE risk | Legal / Compliance | Q1 2025 | Open | Medium | C | - | Doc 5 §6.2
A-405 | Transfer pricing | Document stand-alone credit analysis for German intercompany loan (BFH I R 4/17 — no implicit group support) | F&S / KPMG | Q2 2025 | Open | Medium | C | - | Doc 8 §6.3
A-501 | RWI / SPA | Negotiate specific indemnity/escrow for German FY19-21 audit contingent (€2.4M) — excluded from RWI as known issue | Hargrove & Lund / Deal team | Pre-closing | Critical | High | P | - | Doc 12 Priority 4; Doc 20
A-502 | RWI / SPA | SPA rep: confirm neither German entity holds direct/indirect German real property (GrESt §1(2b)); obtain Grundbuch confirmation | F&S / Deal team | Pre-closing | Open | Medium | P | - | Doc 8 §9
A-503 | RWI / SPA | SPA rep on IP change-of-control consents (IP license agreements §14.2 — >50% UBO change); obtain intragroup waiver/consent or amendment | Hargrove & Lund / IP counsel | Pre-closing | Open | High | P | - | Doc 2 §IV.A
A-504 | RWI / SPA | Confirm RWI binder scope, retentions, and known-issue exclusions (Doc 20: $50M limit, 1% retention) | Hargrove & Lund | Pre-closing | Open | Medium | P | - | Doc 20
A-601 | DAC6 / reporting | Complete DAC6 analysis: Hallmarks C (commenced), D & E (not started); intermediary/taxpayer allocation; filing conclusion for LU & NL | Hargrove & Lund / LU & NL counsel | Pre-closing | Critical | High | P | - | Doc 23 (incomplete)
A-602 | DAC6 / reporting | File any reportable arrangement within 30 days of trigger event (made available / ready / first step) in LU & NL | LU & NL counsel | At trigger | Open | High | C | A-601 | Doc 23 §III
A-603 | DAC6 / reporting | Maintain CbCR data quality for transitional safe harbor; confirm CbCR filing responsibility (Meridian group >€750M revenue) | Group Tax / Finance IT | Ongoing | Open | Medium | C | - | Doc 5 §5.3; Doc 8 §6.1
A-701 | Phase 2 — Irish IP | Commission Irish KDB qualification & nexus analysis BEFORE any IP migration (nexus fraction may be <100%) | Irish advisor / Group Tax | FY2026 | Deferred | High | P2 | A-202 | Doc 24 §5
A-702 | Phase 2 — Irish IP | Quantify Dutch exit charge on IP migration (FMV €55M − TBV €42M = ≥€13M gain → €3.35M CIT) & Innovation Box interaction | Van Steenbergen | FY2026 | Deferred | High | P2 | - | Doc 24 §5.4 (gap)
A-703 | Phase 2 — Irish IP | Assess Swedish CFC risk of Irish KDB (6.25% < 11.22% SE threshold) — could negate entire benefit | Lindström & Partners | FY2026 | Deferred | High | P2 | - | Doc 24 §5.4 (gap)
A-704 | Phase 2 — Pillar Two | Implement GloBE data collection; evaluate QDMTT (NL/LU/SE/DE enacted; SG expected FY2025); monitor €750M threshold (~FY2029-32) | Group Tax / Finance IT | FY2027 | Deferred | High | P2 | - | Doc 5 §5
A-705 | Phase 2 — Pillar Two | Cost-benefit of maintaining Luxembourg layer post-Pillar Two (0.2% ETR → top-up); consider simplification | Group Tax / Advisors | FY2027-28 | Deferred | Medium | P2 | - | Doc 5 §5.3

## Pre-Closing Checklist
PRE-CLOSING TAX CONDITION PRECEDENTS / KEY ACTIONS
Hard blockers to closing & signing. Tick when complete.
# | Action | Required by | Done? | Owner
B-001 | Stille Reserven analysis (German §8c) commissioned & outcome reflected in price/escrow | SPA execution | ☐ | F&S / Deal team
B-002 | Financial model corrected (Singapore 17%; Swedish standalone-EBITDA disallowance); IRR re-underwritten | SPA execution | ☐ | Deal Analytics
B-003 | Debt placement decision (Option A: retain at BidCo) confirmed with lenders & Dutch counsel | Closing | ☐ | Osei-Mensah / Lenders
B-004 | Acquiring fund identity confirmed (Meridian IV vs MonteCedro) and SPA parties aligned | SPA execution | ☐ | Deal team
B-005 | Entity register reconciled with Group Legal | SPA execution | ☐ | Subramaniam
B-006 | Specific indemnity/escrow for German €2.4M audit contingent negotiated | SPA execution | ☐ | Hargrove & Lund
B-007 | Grundbuch search — confirm no German real property (GrESt) | Closing | ☐ | F&S
B-008 | IP license change-of-control consents obtained/waiver mechanism agreed | Closing | ☐ | IP counsel
B-009 | DAC6 analysis completed; filing determination for LU & NL | Closing | ☐ | LU & NL counsel
B-010 | RWI binder bound ($50M, 1% retention); known-issue exclusions confirmed | Closing | ☐ | Hargrove & Lund
B-011 | Tax structuring memorandum delivered to lenders (CP #9: Art.10a CITA non-applicability confirmed) | Closing | ☐ | Hargrove & Lund
B-012 | KPMG updated TP study (Doc 11) finalized & adopted as single source | Closing | ☐ | KPMG / Group Tax